Implementation Roadmap

Four Corners Village

Phased Development Plan & Resource Requirements

—————  ⚙  —————

March 2026 - March 2028

# Project Overview

This roadmap outlines the phased development of Four Corners Village, a multi-tenant digital wellness marketplace. The implementation follows a hybrid approach: rapid deployment using proven WordPress/BuddyBoss infrastructure (Phase 1), followed by strategic decoupling and custom development (Phases 2-3).

## Strategic Approach

- Phase 1: Hybrid WordPress Build (Months 1-6) - MVP launch with existing tools

- Phase 2: Platform Expansion (Months 7-12) - Custom microservices, mobile apps

- Phase 3: Full Decoupling (Months 13-24) - Headless architecture, proprietary frontend

## Timeline Summary

| Phase | Focus | Duration | Key Deliverable |
| --- | --- | --- | --- |
| Phase 1 | MVP & Launch | 6 months | 500 practitioners |
| Phase 2 | Scale & Expand | 6 months | 2,000 practitioners |
| Phase 3 | Optimize & Decouple | 12 months | 10,000 practitioners |

# Phase 1: Proof of Concept (Months 1-6)

Objective: Rapidly deploy a functional MVP using WordPress + BuddyBoss + Directorist to validate the multi-tenant marketplace model and acquire first 500 practitioners.

## Month 1-2: Foundation Setup

- WordPress multisite installation and configuration

- BuddyBoss Platform + Spaces Engine integration

- Directorist directory plugin setup with custom fields

- Stripe Connect integration (Express accounts)

- Zoom API integration for basic meeting scheduling

## Month 3-4: Core Features Development

- Four Directions navigation UI implementation

- Three-tier subscription system (WC Vendors Pro)

- SSO between public directory and private app

- Automated onboarding workflows (Uncanny Automator)

- Basic practitioner dashboard and analytics

## Month 5-6: Launch Preparation

- Digital altar feature (custom plugin)

- Lunar calendar integration

- Security audit and HIPAA compliance review

- Beta testing with 50 pilot practitioners

- Public launch and marketing campaign

## Phase 1 Deliverables

| Deliverable | Timeline | Success Criteria |
| --- | --- | --- |
| MVP Platform | Month 4 | Core features functional |
| Beta Launch | Month 5 | 50 active practitioners |
| Public Launch | Month 6 | 500 practitioners, $30K MRR |

# Phase 2: Proprietary Expansion (Months 7-12)

Objective: Scale to 2,000 practitioners while building proprietary microservices for spiritual features and preparing for custom mobile app development.

## Month 7-8: Advanced Features

- AI Oracle system (OpenAI API + custom tarot decks)

- Astrological matching algorithm (Swiss Ephemeris)

- Advanced analytics dashboard for practitioners

- Native mobile app development begins (React Native)

## Month 9-10: Infrastructure Scaling

- Database optimization and caching layer (Redis)

- CDN implementation for global content delivery

- Zoom Enterprise sub-account automation

- Advanced Stripe Connect workflows (Separate Charges)

## Month 11-12: Mobile & Growth

- iOS and Android app beta release

- Push notification system with lunar triggers

- Referral program and growth loops

- Enterprise sales for Sanctuary tier

## Phase 2 Milestones

| Milestone | Target Date | Metric |
| --- | --- | --- |
| AI Oracle Launch | Month 8 | 10K daily readings |
| Mobile App Beta | Month 11 | 5K beta users |
| Phase 2 Complete | Month 12 | 2K practitioners, $150K MRR |

# Phase 3: Full Decoupling (Months 13-24)

Objective: Transition to fully custom architecture with headless WordPress backend and proprietary React Native frontend, achieving 10,000+ practitioners and enterprise scalability.

## Month 13-16: Architecture Redesign

- GraphQL API layer over WordPress database

- Custom Node.js microservices for core functions

- React Native app rewrite with Four Directions UI

- Real-time features (WebSockets for live events)

## Month 17-20: Enterprise Features

- White-label customization engine

- Advanced API access and webhooks

- Multi-language support (i18n)

- Enterprise SSO (SAML 2.0, OIDC)

## Month 21-24: Optimization & Scale

- Performance optimization (sub-100ms API response)

- Global infrastructure expansion

- Machine learning personalization engine

- Strategic partnerships and integrations

## Phase 3 Target State

| Component | Technology | Status |
| --- | --- | --- |
| Backend | Headless WordPress + Node.js | Migrated |
| Frontend | React Native (iOS/Android) | Native |
| Database | PostgreSQL + Redis | Scaled |
| Infrastructure | AWS/GCP Multi-region | Global |

# Resource Requirements

## Team Structure

| Role | Count | Phase | Responsibility |
| --- | --- | --- | --- |
| Product Manager | 1 | All | Roadmap, prioritization |
| Tech Lead | 1 | All | Architecture, code review |
| Full-Stack Developers | 3 | 1-2 | WordPress, PHP, React |
| Mobile Developers | 2 | 2-3 | React Native, iOS/Android |
| Backend Engineers | 2 | 2-3 | Node.js, PostgreSQL |
| UX/UI Designer | 1 | All | Design system, prototypes |
| DevOps Engineer | 1 | 2-3 | Infrastructure, CI/CD |
| QA Engineer | 1 | All | Testing, automation |

## Budget Breakdown

| Category | Phase 1 | Phase 2 | Phase 3 |
| --- | --- | --- | --- |
| Personnel | $450K | $600K | $900K |
| Infrastructure | $30K | $60K | $150K |
| Third-party APIs | $20K | $40K | $80K |
| Marketing | $100K | $200K | $400K |
| Legal/Compliance | $50K | $50K | $100K |
| Contingency | $100K | $100K | $200K |
| Total | $750K | $1.05M | $1.83M |

# Risk Management

## Key Risks & Mitigation

| Risk | Level | Mitigation Strategy |
| --- | --- | --- |
| Technical Debt | Medium | Code reviews, refactoring sprints, documentation |
| User Adoption | Medium | Beta program, practitioner incentives, onboarding optimization |
| Competition | Low | Unique features, community moat, first-mover advantage |
| Compliance | Medium | HIPAA audit, GDPR compliance, legal review |
| Scaling Issues | Medium | Load testing, caching, CDN, database optimization |
| Key Person Risk | Low | Documentation, cross-training, knowledge sharing |

# Success Metrics & KPIs

## North Star Metrics

- Monthly Recurring Revenue (MRR) - Primary growth indicator

- Practitioner Retention Rate - Target: 85%+ annual retention

- End User Engagement - DAU/MAU ratio target: 30%+

## Phase-Specific KPIs

| Metric | Phase 1 Target | Phase 2 Target | Phase 3 |
| --- | --- | --- | --- |
| Practitioners | 500 | 2,000 | 10,000 |
| End Users | 5,000 | 25,000 | 100,000 |
| MRR | $30K | $150K | $750K |
| Retention | 80% | 85% | 90% |
| NPS Score | 40+ | 50+ | 60+ |

## Review Cadence

- Weekly: Sprint reviews, bug triage, blocker resolution

- Monthly: KPI review, roadmap adjustment, resource planning

- Quarterly: Strategic review, board updates, major pivots

This roadmap is a living document and will be updated based on market feedback, technical learnings, and business priorities.